## Sheet1
ID | Type | Title | Description | Impact | Likelihood / Severity | Owner | Status | Mitigation / Resolution | Date Logged | Target Resolution Date
R1 | Risk | API Dependency Delays | Delays in backend team delivering API for schedule tab | UI implementation | High | Frontend PM | Open | Coordinate with backend team and set hard integration deadlines | 2024-01-12 | 2024-01-22
R2 | Risk | Weekend Schedule Ambiguity | Riders may misinterpret weekend timing if design is unclear | User experience | Medium | UX Lead | Mitigated | Added clear “Saturday/Sunday” tabs in design | 2024-01-15 | 2024-01-19
I1 | Issue | Incorrect Wait Time Display | Wait time logic was showing outdated values | Core functionality | High | Dev Team | Resolved | Fixed time sync and cache refresh issues in Sprint 4 | 2024-02-12 | 2024-02-15
I2 | Issue | Push Notification Delay in Android | Notifications triggered late for Android users | Push alert reliability | Medium | QA Lead | In Progress | Investigating FCM settings and device-specific limitations | 2024-03-04 | 2024-03-10
R3 | Risk | App Store Review Rejection | New tabs and alerts might cause confusion and lead to rejection | Release timeline | Low | PM | Open | Align features with platform guidelines and do a review checklist | 2024-03-10 | 2024-03-20
I3 | Issue | Schedule Tab Not Scrollable on iOS | On smaller devices, schedule tab UI breaks and does not scroll | Accessibility/UX | Medium | Dev Team | Resolved | Fixed responsive design issue in Sprint 5 | 2024-03-15 | 2024-03-18