## Slide 1: Transit Phone Application Sprint Planning Deck
Product Improvement Case Study
Praneeth Koduru

## Slide 2: Sprint Planning Overview
Project Name: Transit App Real-Time Upgrade
Team: Cross-functional Agile team
Duration: 8 Sprints
Release Phases:
Phase 1 → Sprints 1–3 (MVP)
Phase 2 → Sprints 4–6 (UX + Discoverability)
Phase 3 → Sprints 7–8 (Notifications + Polish)

## Slide 3: Sprint 1 – Planning
Theme: Real-Time Location Accuracy (Part 1)
Primary Epics: SCRUM-1
Key User Stories:
SCRUM-6: Accurate Location Tracking
Tasks:
SCRUM-23: Integrate GPS polling mechanism
SCRUM-24: Map rendering of live transit updates
SCRUM-25: Backend endpoint for location feeds
SCRUM-26: QA Test: Real-time location behavior

## Slide 4: Sprint 2 – Planning
Theme: Real-Time Location Accuracy (Part 2)
Primary Epics: SCRUM-1
Key User Stories:
SCRUM-7: Updated ETA Estimates
Tasks:
SCRUM-27: Audit current ETA logic
SCRUM-28: Improved ETA prediction algorithm
SCRUM-29: Update UI for real-time ETA display
SCRUM-31: End-to-end QA testing of ETA accuracy & UX

## Slide 5: Sprint 3 – Planning
Theme: UI/UX Redesign (Part 1)
Primary Epics: UI/UX Redesign (Part 1)
Key User Stories:
SCRUM-9: Clean UI Layout
Tasks:
SCRUM-32: Conduct UI audit & identify inconsistencies
SCRUM-33: Redesign key screens for simpler navigation
SCRUM-34: Implement UI changes across key screens

## Slide 6: Sprint 4 – Planning
Theme: UI/UX Redesign (Part 2)
Primary Epics: SCRUM-2
Key User Stories:
SCRUM-10: Consistent Map Zoom
Tasks:
SCRUM-35: Investigate current map behavior
SCRUM-36: Update map zoom logic
SCRUM-37: Zoom interaction testing across devices

## Slide 7: Sprint 5 – Planning
Theme: Nearby Stops & Route Discovery (Part 1)
Primary Epics: SCRUM-3
Key User Stories:
SCRUM-11: Nearby Stop Finder
Tasks:
SCRUM-38: Fetch and filter nearby stops
SCRUM-39: Design nearby stops map/list UI
SCRUM-40: Tap-to-view service frequency
SCRUM-41: Validate nearby stop accuracy
SCRUM-42: Stop-selection event handler

## Slide 8: Sprint 6 – Planning
Theme: Route Discovery & Student Verification (Part 2)
Primary Epics: SCRUM-3, SCRUM-4
Key User Stories:
SCRUM-12: Route Clarity by Stop
Tasks:
SCRUM-43: Fetch and display route details
SCRUM-44: Build route info UI component
SCRUM-45: QA for route clarity feature
SCRUM-46: Student verification prompt on login
SCRUM-47: Student verification flow

## Slide 9: Sprint 7 – Planning
Theme: Push Alerts + Wait Times
Primary Epics: SCRUM-5
Key User Stories:
SCRUM-15: Accurate Wait Times
SCRUM-16: Weekend Timing Clarity
Tasks:
SCRUM-55–57: Wait time logic + UI
SCRUM-58: Weekend schedule fetch
SCRUM-59: Schedule tab design

## Slide 10: Sprint 8 – Planning
Theme: Premium Info + Upgrade Flow
Primary Epics: SCRUM-5
Key User Stories:
SCRUM-13: Student Subscription Prompt
SCRUM-14: Premium Features Explained
Tasks:
SCRUM-52: Link upgrade CTA (In Progress)
SCRUM-53: Validate copy & feature list (In Progress)
SCRUM-60: Sync schedule tab with real-time updates
SCRUM-61: QA weekend timing display
SCRUM-50: Design feature comparison UI
SCRUM-51: Implement comparison screen
SCRUM-49: QA test student flow
SCRUM-48: Display discount fare eligibility info