## Slide 1: Transit Phone Application Sprint Retrospectives
Product Improvement Case Study
Praneeth Koduru

## Slide 2: Sprint 1 – Retro
What went well:
Successfully integrated accurate GPS tracking
Backend and frontend teams coordinated effectively
All sprint goals completed on time
What can be improved:
QA involvement came in too late in the sprint
Map rendering performance could be better tested on low-end devices
Action Items:
Involve QA from day 1 of the sprint
Add device-level performance checks in QA checklist

## Slide 3: Sprint 2 – Retro
What went well:
ETA accuracy significantly improved with new algorithm
UI updates for ETA display well-received
End-to-end QA testing was thorough
What can be improved:
Initial analysis of ETA logic took longer than expected
Need better documentation on ETA calculation rules
Action Items:
Start discovery tasks earlier (even pre-sprint)
Create shared doc for ETA logic and assumptions

## Slide 4: Sprint 3 – Retro
What went well:
UI audit helped standardize design patterns
Navigation flow was simplified effectively
Design-to-dev handoff was smooth
What can be improved:
Too many UI stories bundled together
Some components lacked responsive testing
Action Items:
Break down large UI changes into smaller deliverables
Add responsive behavior tests to checklist

## Slide 5: Sprint 4 – Retro
What went well:
Zoom functionality improved significantly
Device testing surfaced critical interaction issues
Cross-browser testing started proactively
What can be improved:
Requirements for zoom behavior were unclear initially
Late UI feedback added pressure
Action Items:
Define zoom interaction flows before dev starts
Lock feedback deadline earlier in sprint

## Slide 6: Sprint 5 – Retro
What went well:
Nearby stop discovery worked across GPS scenarios
Stop-to-route linkages were accurate
UI map/list toggles were intuitive
What can be improved:
API responses varied across test data
Need more test coverage on different transit zones
Action Items:
Add mock data for edge-case testing
Work with transit data team for input validation

## Slide 7: Sprint 6 – Retro
What went well:
Route info + direction data was well integrated
Student verification flow is functional and simple
All planned tasks completed
What can be improved:
Verification prompt logic had backend sync issues
Too many last-minute front-end fixes
Action Items:
Improve API documentation for auth flows
Schedule frontend-API sync meeting mid-sprint

## Slide 8: Sprint 7 – Retro
What went well:
Dynamic wait time refresh worked well
Feature comparison screen was clear and useful
QA testing was finished on time
What can be improved:
Wait time logic had discrepancies in edge cases
Not enough design review before dev started
Action Items:
Improve logic fallback when data is missing
Ensure design sign-off before development begins

## Slide 9: Sprint 8 – Retro
What went well:
Good planning and breakdown of UI vs backend tasks
Copy updates were clear and localized
Test coverage was comprehensive
What can be improved:
Too many unfinished stories rolled over
Weekend schedule integration lacked mock support
Action Items:
Split large epics across sprints earlier
Introduce API mocking to decouple front-end testing